## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER
PROJECT NAME
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
TEAM MEMBERS | Team Mamber Name 1
Team Member Name 2
Team Member Name 3
Team Member Name 4
Team Member Name 5

## Status
PROJECT NUMBER | 3
PROJECT NAME | Asset management system
PROJECT MENTOR (sponsor) | Pranav Gupta
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Pranav(TA) | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | Mrudani | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client meeting | Coordination | Arnav | 2 | 1.5 | Done |  | 0.5 | 33.3333
Research existing technology | Preparation | Nidhish,Arnav,Mrudani | 3 | 3.5 | Done |  | -0.5 | 14.2857
Team Meeting | Coordination | Mrudani | 1 | 2 | Done |  | -1 | 50
Learning Mern | Preparation | Nidhish,Arnav,Mrudani,Apeksha,Bhavya | 6 | 8 | Ongoing
Status tracker | Documentation | Apeksha | 1 | 1 | Done |  | 0 | 0
MoM | Documentation | Apeksha | 1.5 | 1 | Done
Week 2 (January 22 - January 28)
Figma | Preparation | Mrudani | 1.5 | 1 | Ongoing |  | 0.5 | 50
Figma | Preparation | Apeksha | 1.5 | 1 | Ongoing
Figma | Preparation | Arnav | 1 | 1 | Ongoing
Figma | Preparation | Nidhish | 1 | 1 | Ongoing
Next client meeting coordination, meeting prep | Preparation | Bhavya | 2 | 2 | Done |  | 0 | 0
Team Meeting | Coordination | Mrudani | 1 | 1.5 | Done |  | -0.5 | 33.3333
Status tracker | Documentation | Apeksha | 1 | 1 | Done |  | 0 | 0
Project Synopsis Writeup | Documentation | Nidhish | 3 | 2 | Done |  | 1 | 50
Project Requirements doc | Documentation | Arnav | 3 | 3.5 | Done |  | -0.5 | 14.2857
MoM | Documentation | Bhavya | 2 | 2 | Done |  | 0 | 0
Week 3 (January 29 - February 4)
SQL connecting to JS (learning) | Preparation | Arnav | 3 | 2 | Done |  | 1 | 50
Understanding Changes Suggested | Preparation | Apeksha | 2 |  | Delayed | Waiting for Client Response
Status tracker update | Documentation | Bhavya | 1 | 1 | Done |  | 0 | 0
Week 4 (Feburary 5 - Feburary 12)
Internal Team Meet | Coordination | Apeksha | 1 | 1 | Done | Work Distribution Done (frontend) | 0 | 0
Figma Updates | Preparation | Mrudani,Arnav | 1 | 1 | Done | New pages had to be added
Database Schema Design | Design | Nidhish,Bhavya | 1 | 1 | Ongoing | Waiting for Client response for Report Generation
Client Follow Up | Coordination | Mrudani | 0.5 | 0.5 | Planned | One Call Done, Will call on 10
Learning ORM | Preparation | Nidhish, Arnav | 2 |  | Planned
Status Tracker | Documentation | Bhavya | 1 | 1 | Done
Frontend Page Design - Login, Dashboard | Development | Apeksha | 3 |  | Planned
Frontend Page Design - Adding Assets, Viewing Assets, User Details | Development | Bhavya , Mrudani | 3 |  | Planned
Frontend Page Design - Adding Project, Viewing Project, Add person | Development | Nidhish, Arnav | 3 |  | Delayed
MoM | Documentation | Apeksha,Mrudani | 1 | 1 | Done
Client Meeting | Coordination | Nidhish | 1.5 |  | Done
Week 5 (Feburary 13 - Feburary 20)
Frontend Page Design (FPD) -Login, Dashboard | Development | Apeksha | 2 | 2 | Done |  | 0 | 0
Frontend Page Design - Adding Assets, Viewing Assets, User Details | Development | Bhavya, Mrudani | 3 | 2 | Done |  | 1 | 50
Frontend Page Design - Adding Project, Viewing Project, Add person | Development | Nidhish, Arnav | 3 | 2 | Delayed |  | 1 | 50
Client Follow Up | Coordination | Bhavya, Arnav | 0.5 | 0.5 | Done |  | 0 | 0
MOM | Preparation | Nidhish, Bhavya | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | Bhavya | 0.5 | 0.5 | Done |  | 0 | 0
Learning Local SQL Mongo | Preparation | Mrudani, Apeksha | 2 |  | Planned
Week 6 (Feburary 21 - Feburary 26)
Frontend Page Design - Adding Project, Viewing Project, Add person | Development | Nidhish, Arnav | 3 | 2 | Delayed |  | 1 | 50
Shared SRS with Client | Coordination | Bhavya | 0.5 | 0.5 | Done |  | 0 | 0
Different CSS stylings check up | Development | Nidhish | 1 | 1 | Done |  | 0 | 0